## Лист1
ERASMUS+ PROGRAMME, KEY ACTION 2
CAPACITY BUILDING IN HIGHER EDUCATION
Connecting universities-industry through smart entrepreneurial cooperation and competitive intelligence of students in Moldova, Georgia and Armenia
Project nº
CONNECT PROJECT'S TIMELINE
Nr. | Month | WP1 Preparation /MSU | WP 2 Development/UNATC | [10 empty] | WP 3 Development/ RISEBA |  |  | WP 4 Development /ILIE | [12 empty] | WP5 Dissemination/ NGO IMPULS | [8 empty] | WP 6 Qty control and monitoring | [5 empty] | WP7 Management/MSU
0 |  |  |  |  | 2.2 Trained staff in the delivery of the courses on hard and soft skills (acceleration programme, digital skills, theatre and dance) | [8 empty] | 3.1 Arranged inspiring physical spaces | 3.2 Procured & installed equipment | 3.3 Created MOOC | [7 empty] | 4.5 Interconnected university-enterprise systems through joint activities | [5 empty] | 5.1 Dissemination and Exploitation Strategy | 5.3 Web site developed | 5.4 Testemonials and marketing materials | [6 empty] | Qty assurance and monitoring roadmap | [5 empty] | Management roadmap | Financial Management | Human capacity management | Time management | Communication and meetings | Internal monitoring
1 | /JAN-2021
2 | FEB-2021 | 1.1 Project Management Plan | [46 empty] | x
3 | MAR-2021 | 1.2 Launch meeting in Moldova, and forward plan future meetings | 2.1 Integrated report on findings | Design and organise study-visits at each EU partner
4 | APR-2021 | 1.3 Terms of reference for Advisory Group and External Evaluator |  |  |  | 1st training workshop on-line + recorded videous | 2 d evaluation wshop in Moldova | 2 d evaluation wshop in Armenia | 2 d evaluation wshop in Georgia | 2.3 Created courses (hard copy) structure, content& materials (acceleration, digital, arts)
5 | MAY-2021 |  |  |  |  | 2nd training workshop on-line + recorded videous |  |  |  |  | Support course 1 | Support course 2 | Support course 3
6 | JUNE-2021 |  |  |  |  | 3rd training workshop on-line +recorded videous | [26 empty] | 5.2 University Breakfast networking events | 5.5 Inter-university delivery Network | 5.6 Train the trainers’ sessions for non-project partners HEIs in EaPC | 5.7 Signed collaboration agreements between HEIs-companies | 5.8 Peer to peer workshops | 5.9 Presentations and publications |  |  | Internal review | feedback of direct beneficiaries | Advisory Group/ Associated partners who give their evaluation of the products/resutls
7 | JUL-2021 |  |  |  |  | 4th training workshop on-line + recorded videous | [24 empty] | Maintenance of the web-site | Testemonials and marketing materials printed and disseminated | [11 empty] | x /progress reports |  |  |  |  | x
8 | AUG-2021
9 | SEPT-2021
10 | OCT-2021
11 | NOV-2021
12 | DEC-2021 | [15 empty] | 4.1 Implemented courses on acceleration programme for for all interested students, future start-ups and incorporated companies (MOOC + SMARTCHANNEL) | 1st time
13 | /JAN-2022 | [17 empty] | 4.2 Implemented courses on digital skills for all interested students, future start-ups and incorporated companies (3 times repeated) (MOOC + SMARTCHANNEL) | 1st time | 4.3 Implemented courses on theatre and dance for all interested students, future start-ups and incorporated companies | 1st time | 4.4 Embedded new approaches in the curricular of HEIs
14 | FEB-2022 | [42 empty] | x /progress reports
15 | MAR-2022 | [47 empty] | x
16 | APR-2022 | [16 empty] | 2nd time
17 | MAY-2022 | [18 empty] | 2nd time |  | 2nd time | [16 empty] | Preparation for the reporting
18 | JUNE-2022 | [38 empty] | Appointment of an external evaluator
19 | JUL-2022
20 | AUG-2022 | [16 empty] | 3rd time | [25 empty] | x /progress reports
21 | SEPT-2022 | [18 empty] | 3rd time |  | 3rd time | [16 empty] | M21 -1st reporting | [9 empty] | x
22 | OCT-2022
23 | NOV-2022
24 | DEC-2022
25 | /JAN-2023
26 | FEB-2023 | [23 empty] | 4.6 Competition – experimentation and learning by doing (together with companies) | Preparation
27 | MAR-2023 | [42 empty] | x /progress reports
28 | APR-2023 | [47 empty] | x
29 | MAY-2023 | [24 empty] | 1 in Moldova |  |  | Preparation for the Pitch Competition
30 | JUNE-2023 | [25 empty] | 1 in Armenia
31 | JUL-2023 | [26 empty] | 1 in Georgia
32 | AUG-2023
33 | SEPT-2023
34 | OCT-2023 | [27 empty] | Pitch Competition
35 | NOV-2023
36 | DEC-2023 | [47 empty] | x
36 | /JAN-2024